## Tasks
Project Tracker — Project Orion
Contoso Electronics · PMO · Snapshot date: 2026-04-06
Task ID | Task Name | Owner | Sprint | Priority | Status | Due Date | Progress % | Dependency | Risk
TSK-2001 | Finalize integration pattern for Sales module | R. Kumar | Sprint 3 | High | Done | 2026-03-20 | 100% | — | None
TSK-2002 | Migrate legacy customer master data | S. Liu | Sprint 4 | High | In Progress | 2026-04-18 | 60% | Task ID 1 | Data quality issues may extend timeline
TSK-2003 | Build Finance general ledger workflows | A. Verma | Sprint 4 | High | In Progress | 2026-04-25 | 45% | — | None
TSK-2004 | Configure Supply Chain reorder-point alerts | D. Osei | Sprint 5 | Medium | Not Started | 2026-05-02 | — | Task ID 2 | Depends on data migration completing first
TSK-2005 | Complete Security Assessment remediation | E. Marsh | Sprint 4 | High | In Progress | 2026-04-10 | 70% | — | Two high-risk findings still open
TSK-2006 | Deploy Deployment Readiness monitoring tools | K. Ibrahim | Sprint 5 | High | Not Started | 2026-05-09 | — | — | Awaiting delayed Dell hardware shipment
TSK-2007 | Build Procurement approval routing workflow | R. Kumar | Sprint 5 | Medium | In Progress | 2026-05-06 | 30% | — | None
TSK-2008 | User Acceptance Testing — Sales module | S. Liu | Sprint 6 | High | Not Started | 2026-05-20 | — | Task ID 1 | Depends on Sales module build completing
TSK-2009 | User Acceptance Testing — Finance module | A. Verma | Sprint 6 | High | Not Started | 2026-05-27 | — | Task ID 3 | None
TSK-2010 | Draft end-user training materials | D. Osei | Sprint 5 | Medium | In Progress | 2026-04-30 | 40% | — | Training schedule not yet finalized
TSK-2011 | Configure role-based executive dashboards | E. Marsh | Sprint 5 | Medium | Not Started | 2026-05-13 | — | — | None
TSK-2012 | Vendor scorecard tracking build (Procurement) | K. Ibrahim | Sprint 6 | Low | Not Started | 2026-06-03 | — | Task ID 7 | None
TSK-2013 | Disaster recovery test — Finance data | R. Kumar | Sprint 6 | High | Not Started | 2026-06-01 | — | Task ID 6 | Depends on monitoring tools deployment
TSK-2014 | Teams/SharePoint notification integration | S. Liu | Sprint 4 | Medium | Done | 2026-03-28 | 100% | — | None
TSK-2015 | Contract renewal reminder automation (Procurement) | A. Verma | Sprint 6 | Low | Not Started | 2026-06-10 | — | — | None
TSK-2016 | Load testing — multi-warehouse inventory | D. Osei | Sprint 6 | Medium | Not Started | 2026-06-05 | — | Task ID 4 | None
TSK-2017 | Finalize data-retention configuration | E. Marsh | Sprint 5 | Medium | In Progress | 2026-05-01 | 20% | — | None
TSK-2018 | Go-live cutover runbook draft | K. Ibrahim | Sprint 6 | High | Not Started | 2026-06-15 | — | — | Depends on all UAT sign-offs
TSK-2019 | Hypercare support plan and staffing | R. Kumar | Sprint 6 | Medium | Not Started | 2026-06-12 | — | — | None
TSK-2020 | Post-go-live 90-day success metrics dashboard | S. Liu | Sprint 7 | Low | Not Started | 2026-07-15 | — | — | None
| Summary: |  |  |  | 2
Tasks marked "Done" above (of 20):